## ART
LITTLE BENTO (WIP TITLE) ---- ART |  |  | ASSET FOLDER
TEAM: Clodial, Freya, Lonk, Maddie, Lack
TASK | PRIORITY | STATUS | NOTES | TEAM | START DATE | END DATE | DUE DATE
Guide - Yuki Ghost | ----- | Done | need to adjust angle | Freya | 2024-01-22
Grilling station — Fish | ----- | Done
Grilling station — Egg | ----- | Done
Player - Kora | ----- | Done | 1/22: temp | Freya | 2024-01-22
Prep station — Rice | ----- | Done
Prep station — Salad | ----- | Done
Square Bento - 2 x 2 (1ct) | ----- | Done | Base 2x2 square bento - Top view 500 x 500px |  | 2024-01-24 | 2024-01-24
Floor plan | ----- | Done | 6x6 Playable Grid ISO View | Freya | 2024-01-22 | 2024-01-22
Floor tile design | ----- | Done |  | Freya
Kitchen Background | Low | In-progress | shoji screens and cooking tools on opposite wall | Freya
Handoff Station (3ct) | ----- | Done | counter_right.png | Freya
Customer - Old Timer | ----- | Done | Red Marker - face North West - sillohoutte | Freya | 2024-01-22 | 2024-01-25
Customer - Salary Man | ----- | Done | Yellow Marker - face North West - sillohoutte | Freya | 2024-01-22 | 2024-01-25
Customer - Young | ----- | Done | Green Marker - face North West - sillohoutte | Freya | 2024-01-22 | 2024-01-25
Inventory Access - Fridge? Button | ----- | Done | blue fridge with photo | Freya
Inventory Item - Rice | ----- | Done | rice sack | Freya
Inventory Item - Egg | ----- | Done | brown egg | Freya
Inventory Item - Fish | ----- | Done | raw fillet | Freya
Inventory Item - Lettuce | ----- | Done | romaine | Freya
Inventory Item - Tomatoes | ----- | Done | generic | Freya
Home Page | ----- | Done |  | Lack
Purchase order window |  |  |  | Lack
Dishes - Cooking, Done, Burnt 1 | ----- | Done |  | Freya
Dishes - Cooking, Done, Burnt 2 | ----- | Done |  | Freya
Dishes - Cooking, Done, Burnt 3 | ----- | Done |  | Freya
Dishes - Cooking, Done, Burnt 4 | ----- | Done |  | Freya
Font Style Choice | ----- | Done |  | Freya
Color Pallet | ----- | Done |  | Freya
Home - Credit | Low
Home - How to Play | Low |  |  | Lack
Home - Logo | Low | Done | arced text | Lack
Emots - Smile | TBD
Emots - Stoic | TBD
Emots - Angry | TBD
Emots - Heart | TBD
Emots - Pissed Off (grumble) | TBD
Emots - Timer Bar Guage Bar | High
Emots - Timer Bar Radial | TBD
UI - Ready, Start, Done | ----- | Done | Final text - ready, start, times up! | Freya | 2024-01-23 | 2024-01-24
UI - Home button |  |  |  | Lack
UI - X button | ----- | Done | x button embedded into graphic unless otherwise | Freya
UI - Cooking Timer | High | In-progress
UI - Health Bar | High | In-progress
UI - Pause + Play | High | In-progress | To pause and unpause the game | Lack
UI - Order up |  |  | Basic Green Checkmark | Lack
UI - Timer | ----- | Done |  | Freya
UI - dialogue box (9-slice) | ----- | Done |  | Freya
UI - Dash -- special move | TBD
UI - dash button up > press and hold to activate | TBD
UI - dash button down | TBD
UI - currency | ----- | Done | japan 1000 yen | Freya
overlay Bento - Complete #1 |  |  | Quardrant of cooked rice top view | Freya
overlay Bento - Complete #2 |  |  | Quadrant for cooked fish top view | Freya
overlay Bento - Complete #3 |  |  | Quadrant of salad top view | Freya
overlay Bento - Complete #4 |  |  | Quadrant of tamago top view | Freya
completed bento box |  |  | a filled bento box on counter. | Lack
Tutorial page | Medium | In-progress |  | Lack
UI - confirm button prompt | High |  | confirm action prompt button whenever the Player stands next to an interactable object. E.G. standing next to a customer or a cooking station. | Lack
UI - salad assembly key prompts | High |  | Generic Up, Down, Left, Right directionals. Nothing too fancy is fine think DDR | Lack

## CODES
PROGRAMMING & GAME DESIGN
TEAM | Clodial, Freya, Lonk, Maddie, Lack
TASK | STATUS | PRIORITY | NOTES | TEAM | START DATE | END DATE | DUE DATE

## WRITING
WRITING | Dialogue List
TEAM | Clodial, Freya, Lonk, Maddie, Lack
TASK | STATUS | PRIORITY | NOTES | START DATE | END DATE | DUE DATE
Character Barks - Tutorial | Done | Low | Need to know keybings | 2024-01-22
Character Barks - Kora Reactions | Done | Medium
Character Barks - Yuki Reactions | Done | Medium
Character Barks - Child Reactions | Done | High
Character Barks - Old Man Reactions | Done | High
Character Barks - Buisnessman Reactions | Done | High
Character Barks - Normal Female Reactions | Don't need | Low
Character Barks - Normal Male Reactions | Don't need | Low
Yuki Letter | Done | Low
Ordering Dialogue |  | Medium | What ingredients do we have, and how will the ordering system work.
Game Outline/Synopsis |  | Medium
Conversations between NPC's | In-progress | High
Wireframe how dialogue will work | Done | High
Tutorial | Done | High | Keybinds are in design doc
Challenge List | Done | High

## SFX
SOUND DESIGN
TEAM | Clodial, Freya, Lonk, Maddie, Lack
TASK | STATUS | PRIORITY | NOTES | START DATE | END DATE | DUE DATE
Kitchen | Done | Medium | AMB
Select | Done | High | UI
Hover | Done | High | UI
Back | Done | High | UI
Blanket Start Station | Done | High | IA
Rice Cooking | Done | Low | AMB
Blanket End Station | Done | High | IA
Fridge Inv Opening | In-progress | Medium | IA
Fridge Inv Closing | In-progress | Medium | IA
Order pop-up! | Done | High | UI
Blanket success state | Done | High | IA
Blanket fail state | Revise | High | IA
Timer countdown | Done | High | UI
Round done! | Done | High | UI
Gain $$ | Done | Medium | UI
Dash |  | High | PC
Bento Delivery | Done | High | IA
Gdma Pop-up! | Done | High | UI